## Sheet1
Sr. No. | Module / Activity | Timeline | Status
1 | Requirement Finalization & Access Handover | 15 Jun – 16 Jun | Done
2 | Firebase Review & Data Migration Planning | 15 Jun – 17 Jun | Done
3 | Merchandise Development | 17 Jun – 20 Jun | WIP
4 | Donation Module Development | 21 Jun – 22 Jun
5 | Varganidaar | 22 Jun – 24 Jun
6 | Payment Gateway Integration (TBD) | 25 Jun – 26 Jun
7 | Admin dashboard and pages | 27 Jun – 30 Jun
8 | Migration Execution & Data Validation | 30 Jun – 01 Jul
9 | Internal Testing & QA | 01 Jul – 02 Jul
10 | UAT (User Acceptance Testing) | 03 Jul – 04 Jul
11 | UAT Fixes & Final Sign-Off | 2026-07-04
12 | Production Deployment & Go-Live | 2026-07-05